## Sheet1
Zombono v0.1.0 (Targeted for 2024-07-30) | Date: 2024-07-30
Task | Area | Completed? | Completion Date
Fix: Warehouse ramps too steep | Bugfix
Fix: "velocity increasing but not speed" (prediction miss bug when hitting wall at specific angle sometimes) | Bugfix
Fix: game connecting to server during intro | Bugfix
Fix: no mouse in menus | Bugfix
Fix: func_train in subway fucked up | Bugfix
Fix: Fucked up chair collision | Bugfix
Fix: Zombification: you can get stuck | Bugfix
Fix: Transferring of physics information | Bugfix
Fix: ! Character | Bugfix
Fix: If there's multiple chat messages already and you're typing it gets offset | Bugfix
Fix: Incorrect update channel description (Release) being pulled on Debug | Bugfix
Fix: Insane stupidity with windowing | Bugfix
Fix: Can never reenter a server if you quit with TeamUI active | Bugfix | Yes
Fix: Legacy UI arrow keys | Bugfix | Yes | 2024-07-18
Fix: Only one localisation key reference works in localisation string | Bugfix
Fix: line -> comment -> line leads to skip in localisation parser? | Bugfix
Fix: input | Bugfix
Complete Release Generation Tool | Engineering | Yes | 2024-06-30
Properly split out client.h, server.h | Refactoring
Add team door brush entity | Feature
De-jankify tangfuslicator jump | Feature, Bugfix
Add kill feed | Feature
Make Master servers work | Feature, Netservices
Add HTTP POST to Netservices | Feature, Netservices | Yes | 2024-08-05
BrowseServersUI | Feature, Netservices
Text Engine - scaled coordinates | Feature
Text Localisation Engine | Feature | Yes | 2024-07-10
Get working waves mode | Feature
Allow people to see what team a player is | Feature
Euphoria Dedicated Server binary | Feature | Yes | 2024-06-30
Real updater (hash based) | Feature
Top down camera and camera rewrite | Feature | Yes | 2024-07-24
z_waves_port working (THEY COME FROM THE SEA/!?!?!?!?!) - z_tdm_spire finished | Content
Get real weapon models | Content
z_tdm_warehouse - Redesign | Content
Finish z_warehouse easter egg | Content
Account, IP ban | Content
Account system incl. Premium | Content
Login API | Content
New main menu | Content
Game trailer | Content
Write ZombonoUI documentation | Documentation
Write Font Engine documentation | Documentation
Write Localisation documentation | Documentation
NOT FINISHED - MORE SOON