## Sheet1
Zombono v0.0.11 (could also be 0.1.0 if we finish anything) | Date: 2024-06-29
Task | Area | Completed? | Completion Date
Fix: Warehouse ramps too steep | Bugfix | Yes | by redesign
Fix: "velocity increasing but not speed" (prediction miss bug when hitting wall at specific angle sometimes) | Bugfix
Fix: game connecting to server during intro | Bugfix
Fix: relative velocity being added multiple times | Bugfix | Yes | 2024-06-11
Fix: func_train in subway fucked up | Bugfix
Fix: Fucked up chair collision | Bugfix
Fix: Zombification: you can get stuck | Bugfix
Fix: Green pipe, add poster there | Bugfix | Yes | 2024-06-13
Fix: Game does not clear entities on 2nd entry into a map | Bugfix | Yes | 2024-06-29
Fix: Alt+tab crash in dedicated fullscreen | Bugfix | Yes | 2024-06-11
Fix: Incorrect update channel description (Release) being pulled on Debug | Bugfix
Complete Release Generation Tool | Engineering
Properly split out client.h, server.h | Refactoring
Gamemodes per-file | Refactoring | Yes
Add team door brush entity | Feature
De-jankify tangfuslicator jump | Feature, Bugfix
Add kill feed | Feature | Yes | 2024-08-10
z_tdm_warehouse - Second Floor | Feature
Make Master servers work | Feature, Netservices
BrowseServersUI | Feature, Netservices
Text Engine - scaled coordinates | Feature
Start Waves mode programming | Feature
Allow people to see what team a player is | Feature
cl_console_line_length | Feature | Yes
Real updater | Feature
Automatically load scaled images | Feature | Yes
Mkpak in binary | Feature | Yes | 2024-06-23 01:24
z_waves_port working (THEY COME FROM THE SEA/!?!?!?!?!) - z_tdm_spire finished | Content
Finish z_warehouse easter egg | Content
NOT FINISHED - MORE SOON