## Sheet1
Zombono v0.0.10 | Date: 2024-06-09
Task | Area | Completed? | Completion Date
Fix: Jumping from a surface must maintain its relative velocity | Bugfix | Yes (but it sucks) | 2024-06-05 00:37
Fix: surface and content flags | Bugfix | Yes | Was map issue
Fix: no lighting on top of subway buildings, slight gap on one of them | Bugfix | Yes | 2024-05-27
Fix: Warehouse ramps too steep | Bugfix | Deferred to 0.0.11
Fix: Machine gun cannot gain more ammo from packs while out of ammo | Bugfix | Yes? | 30/05/2024 (TEST)
Fix: Machine gun infinite ammo if held | Bugfix | Yes | 2024-05-30
Fix: Re-implement SURF_NODRAW (was never originally implemented) | Bugfix | Yes | 2024-05-27
Fix: Missing background and unusual spacing of TimeUI | Bugfix | Yes | 2024-06-03
Fix: Unusual spacing of "SELECT TEAM" text | Bugfix | Yes | 2024-05-29 23:48
Fix: Mouse snapped to (0,0) during intro screen | Bugfix | Yes
Fix: Can still move in TeamUI | Bugfix | Yes | 2024-05-29
Fix " velocity increasing but not speed" (prediction miss bug when hitting wall at specific angle sometimes) | Bugfix | Deferred to 0.0.11
Fix armour | Bugfix | Yes | 2024-06-04
Fix: Game connects to server during intro on Playtest builds | Bugfix | Deferred to 0.0.11
Split qfiles.h - bsp.h, md2.h, sp2.h, pak.h | Refactoring | Yes | 2024-05-26 01:31
Complete Release Generation Tool | Engineering | Deferred to 0.0.11
Add kill feed | Feature | Deferred to 0.0.11
Add map and fps meter to cl_showinfo | Feature | Yes | 2024-05-30
Add Planfuslicator behaviour (fudge reload time) | Feature | Yes | 29/05/2024 (REQUIRES POLISHING)
Add func_particle_effect (Particle Effect Generator Entity) | Feature | Yes | 02/06/2024 (REQUIRES POLISHING)
Add team door brush entity | Feature | Deferred to 0.0.11
Port other UI controls to Zombono UI Engine | Feature | Yes | 05/06/2024 (REQUIRES POLISHING)
Victory and defeat jingles | Feature | Yes | 2024-06-08 17:55
Continue work on z_waves_port, z_tdm_spire, z_waves_yekaterino | Content | Yes
Remodel centre of z_tdm_labrats | Content | Yes | 02/06/2024 (REQUIRES POLISHING)
Finish z_warehouse easter egg | Content | Deferred to 0.0.11